## Risk Assessment
Operational Risk Assessment Template
Purpose: Identify operational risk, assess probability and impact, define mitigation tasks, reassess residual risk after mitigation, assign ownership and track completion.
ID | Risk Description | Probability (Sannsynlighet) | Impact | Initial Risk (P x I) | Risk Level | Mitigation Tasks | Residual Probability | Residual Impact | Residual Risk (P x I) | Responsible / Due Date
1 | Loss of redundancy during UPS maintenance | 3 | 4 | 12 | HIGH | Approved MOP, rollback plan, monitoring active | 2 | 4 | 8 | Operations Lead / Before work
2 | Cooling capacity reduction during maintenance | 3 | 4 | 12 | HIGH | Verify spare capacity and define stop conditions | 2 | 3 | 6 | Facility Operations / Before maintenance
3 | Incorrect asset identified before work | 2 | 5 | 10 | HIGH | Second-person verification and asset tag confirmation | 1 | 5 | 5 | Technical Lead / Before execution
Risk Level Legend
LOW | 1–4
MEDIUM | 5–9
HIGH | 10–16
CRITICAL | 17–25
Best practice principles:
• Define stop conditions before work begins.
• Residual risk should be reassessed after mitigation tasks are applied.
• High and Critical risks should require formal review and approval.
• Risk ownership should be explicit and time-bound.
• Risk assessments should be reviewed after incidents, changes or major maintenance activities.